## New Points
S No | Type | Request Date | Module | Screen | Request Description | Date of Assignment to Tecxpert | Delivered Exe No | Delivered Exe Date | Testing Date | Testing Remarks | User Name | User Confirmation date | Status | Status Tecxpert | Status on 28/04/2017
#REF! | Bug | 2017-03-01 | Production | Production entry | System is showing incorrect FAT/SNF KG in the production entry no. refer to entry no PE-003/16-17/000978. pls correct all the entries & item codes. pls also correct stock reco & production report | 2017-03-02 | 5.1.1.37 | 2017-03-20 | 2017-03-20 | Pending…the mentioned document no is still showing incorrect fat/snf kg | Sandeep |  | Pending
#REF! | Bug | 2017-04-07 | Production | Item Consumption Report | item consumption report is not showing FAT/SNF and rate of all the materials. Refer to the batch order no BO-003/16-17/07/000003 & standardization no STD-003/16-17/001404 in which 824kg of item code SF000020 was consumed. However, item consumption report is not showing fat/snf qty & rate. pls check & correct all the item code | 2017-04-08 |  |  |  |  | Auditor |  | Pending
123 | Bug | 2017-04-13 | Fresh Sale | Price Master | system is not allowing to close posted price master in fresh sale neither it is allowing to save two price master in same date. Pls check | 2017-04-13 |  |  |  |  | Prakash |  | Pending
129 | Bug | 2017-04-13 | Fresh Sale | Fresh Invoice | system created duplicate fresh invoice against dispatch no FDI-003/16-17/123560 to FDI-003/16-17/123612. These invoices have been cancelled by making the document amount zero but print format is still reflecting total amount & the narration "Cancelled due to duplicate entry". Pls do the needful | 2017-04-13 |  |  |  |  | Harish |  | Pending
#REF! | Change | 2017-04-13 | General Ledger | GL Reports | Pls Provide IND AS tick on General ledger report, P&L and Balance sheet filter. The functionality to be same as Trial balance | 2017-04-13 |  |  |  |  | Preeti |  | Pending
#REF! | Change | 2017-04-13 | Dairy Production | Production Reports | Pls provide a summary level report in the item consumption report. The summary should be plant wise production item wise material consumed items. Format is being forwarded by email | 2017-04-13 |  |  |  |  | Sandeep |  | Pending
139 | Bug | 2017-04-19 | MCC Procurement | Village Data | In the village data screen, system is picking the wrong price chart if the rate is effected from the evening | 2017-04-20 |  |  |  |  | Prasanjit |  | Pending | to be checked to be delivered
146 | Bug | 2017-04-20 | Payroll | Salary Generation | Refer to salary generation doc no SALGEN/17-18/000001 to SALGEN/17-18/000006. these document belongs to march 2017, however system is making of document no of 2017-18 period. Pls check | 2017-04-20 |  |  |  |  | Dhananjay |  | Pending
#REF! | Change | 2017-04-22 | Vendor Management | AP invoice Entry | Below changes are required in the AP invoice entry uploader for updating employee wise salary in ERP 1) Provision for capturing 25 GL accounts. Current uploader is only taking five GL account maximum 2) Provision for GL account wise Debit/Credit. | 2017-04-22 |  |  |  |  | Harish |  | Pending

## Done Points
S No | Type | Request Date | Module | Screen | Request Description | Date of Assignment to Tecxpert | Delivered Exe No | Delivered Exe Date | Testing Date | Testing Remarks | User Name | User Confirmation date | Status | Status Tecxpert | Status on 28/04/2017 |  | Kwality Remarks | tester remarks
1 | Change | 2017-01-15 | MCC Procurement | Payment Process | MCC Farmer payment where (Purchase to be booked farmer wise details to be shared). Sale to be booking directly to farmers & uploader is also required for the same | 2017-01-15 | 5.1.1.46 & 5.1.1.57 | 2017-04-17 | 2017-04-17 | 1) farmer payment neft uploader missing 2) prefix is generating for current year even if payment process date is for previous month 3) invoice entries not updating in the farmer ledger after bills are generrated 4) option missing for unselecting farmers of the VSP on mapping screen 5) Sale uploader missing 6) Other Points already given to Ms Nisha | Rohil |  | Pending |  | WIP | Preeti Gupta
2 | Change | 2017-01-15 | Common | All | ERP to be revisited for checking end to end financial & other entries | 2017-01-15 |  |  |  |  | SK Gupta Sir |  | Pending |  | Done
#REF! | Change | 2017-01-15 | Common | All | Prompt message to clear all the pending transaction on the last day of the month. | 2017-01-15 | 5.1.1.37 | 2017-03-20 | 2017-03-20 | Pending…system is not allowing to give the declaration of the pending document. It is showing DB Null error which submitting the declaration. Moreover, it is not showing all the documents of the user. The report is also not there | SK Gupta Sir |  | Pending |  | Done | Kunal | Pending | pending
#REF! | Change | 2017-01-15 | Common | All | Screen for declaration of pending documents on monthly basis | 2017-01-15 | 5.1.1.57 | 2017-04-17 | 2017-04-17 | While log in, system is not showing any declaration screen | SK Gupta Sir |  | Pending |  | Done | Kunal | Pending | pending
#REF! | Change | 2017-01-15 | Material Management | Stock Reco | Main location is not coming in stock reco, document detail level report | 2017-01-15 | 5.1.1.32 & 5.1.1.37 & 5.1.1.46 & 5.1.1.57 | 2017-04-17 | 2017-04-17 | 1) Pending…main location is still not coming in the stock reco. 2) Pending…still not showing main location 3) Pending…main location is still not coming in the stock reco report. Even after deleting Layout 4) Main location still not coming | Auditor |  | Pending | On Setting Based of Latest Stock Reco | Done | Monika | Pending
#REF! | Change | 2017-01-15 | Purchase | Report | PO amendment report is required | 2017-01-15 | 5.1.1.37 & 5.1.1.46 & 5.1.1.57 | 2017-04-17 | 2017-04-17 | 1) Pending…the status column is showing incorrect data. It is showing status close for the open PO. Refer POO-003/16-17/001404. also remove time from the amendment date column 2) Refer to PO no POR-003/16-17/000492. All the line item of this PO are not reflecting on the PO amendment report. The PO has been short closed, however should open in the PO amendment report 3) The report is still not showing correct qty & amount | Naveen |  | Pending | Working fine with new data. To be delivered | Done | Stuti | Pending | done
#REF! | Change | 2017-01-15 | Merchant Trade | Report | Merchant trade report need to be developed | 2017-01-15 |  |  |  |  | Prashant |  | Pending | On Testing | Done | Stuti
#REF! | FOC | 2017-01-15 | Fixed Assets | Fixed Assets | Fixed Asset module | 2017-01-15 |  |  |  |  | Sunny |  | Pending | On Testing | Done | Preeti Gupta
#REF! | FOC | 2017-01-15 | General Ledger | Profit & Loss | P&L and Balance Sheet to be generated from ERP | 2017-01-15 |  |  |  |  | SK Gupta Sir |  | Pending | 15-16 report is not coming | Pending
#REF! | FOC | 2017-01-15 | MCC Procurement | MCC Replication | User defined functionality to be provided for MCC Replication | 2017-01-15 |  |  |  |  | Prasanjit |  | Pending |  | Pending | Panchraj
#REF! | FOC | 2017-01-15 | Common | All | Out of Memory Error on reports | 2017-01-15 |  |  |  |  | Harish |  | Pending |  | R&D
#REF! | FOC | 2017-01-15 | Common | All | High utilization of Memory | 2017-01-15 |  |  |  |  | Harish |  | Pending |  | R&D
#REF! | FOC | 2017-01-15 | Common | All | The balance of FAT Kg & SNF Kg should not be negative | 2017-01-15 | 5.1.1.32 | 2017-03-14 | 2017-03-15 | Pending…when the setting is on, then it is impacting transactions response. | Saching |  | Pending | On Setting Based of Latest Stock Reco and as discussed before 31/03/2017, need to do store adjustment for removing -Ve FAT/SNF | Done
#REF! | FOC | 2017-01-15 | Common | All | Reconciliation report required for sub modules & Finance | 2017-01-15 |  |  |  |  | Manish |  | Pending |  | Pending
#REF! | 204 Pending | 2016-12-31 | Common | All | Attached are the module wise screen names for which unpost / reversal / return functionality is required. Kindly do the needful. Earlier request no KLREQ000356 was cancelled | 2016-12-31 |  |  |  | Pending…updated sheet send via email. | Harish |  | Pending |  | Pending
#REF! | 204 Pending | 2016-12-31 | Material Management | Stock Reco | Date & item wise stock report is not showing for all days therefore all the items are not coming date wise for example it is showing just 3 items on 30 april for delhi. The date range it 30-30 april | 2016-12-31 |  |  |  | Pending...again the fat/snf filter is not working on this report | Harish |  | Pending |  | WIP
#REF! | 204 Pending | 2016-12-31 | Material Management | Stock Reco | stock reco report is not showing FAT/SNF as per final qc details entered in the production entry screen. It is showing fat/snf as per the item master. Kindly resolve it as we arel not able to reconcile physical stock with the ERP stock becasue of this. | 2016-12-31 |  |  |  | Kindly provide a new report for this | Harish |  | Pending | On setting based,new stock reco shown and you can check the QC values when FAT/SNF type is "BOTH" | Done | Monika | Pending
#REF! | 204 Pending | 2016-12-31 | Material Management | Stock Report | pls find attached the consolidated stock report to be develop in ERP. | 2016-12-31 |  |  |  | Pending…this is still pending | Harish |  | Pending | On setting based,new stock reco shown and you can check the consolidates report,when report type is "Transaction Type" | Done | Monika | Pending
#REF! | 204 Pending | 2016-12-31 | Material Management | FAT/SNF Report | WIP Report & Section wise consumption report | 2016-12-31 |  |  |  | Pending | Lokesh |  | Pending | On setting based,new stock reco shown and you can check the when checkbox of "Production WIP" is checked. | Done | Monika | Pending
#REF! | 204 Pending | 2016-12-31 | Vendor Management | Vendor Service Charge | The screen response of screen like Vendor service charge, Transfer (out no finder), branch account mapping, route freight master, Item issue/return entry is very slow. Kindly optimize | 2016-12-31 | 5.1.1.57 | 2017-03-16 | 2017-03-16 | 1) System response still very slow for transfer screen (out no finder), route freight master | Dhananjay |  | Pending |  | Done |  | Pending
#REF! | New Points | 2017-02-10 | Common | All | Provision of GST | 2017-02-10 |  |  |  |  | Sunny |  | Pending |  | Pending
#REF! | Bug | 2017-02-20 | Material Management | Transfer | Refer to the transfer no STI-008/16-17/000171 & 172, the impact of tax is not going to general ledger/trial balance - Clarification – alrady given to Rakesh Sir | 2017-02-20 | 5.1.1.36 |  |  | Pending…journal entry of mentioned transfer no still not showing tax impact | Tribhuvan |  | Pending |  | Client Clarification
#REF! | Bug | 2017-02-20 | Common | All | Stop Negative FAT/SNF qty in report and transaction(WIP) - Done – System still allowing negative transactions –Done – System still allowing negative transactions | 2017-02-20 | 5.1.1.32 | 2017-03-14 | 2017-03-14 | 1) Pending… this has been revert back as it was impacting the Fresh sale posting process | Sachin |  | Pending | 1) Pending… this has been revert back as it was impacting the Fresh sale posting process
#REF! | Bug | 2017-02-20 | Vendor Management | Vendor Service Charge | The screen response of vendor service charge screen is very slow while working on VPN - WIP | 2017-02-20 |  |  |  |  | Dhananjay |  | Pending | Duplicate | Duplicate
#REF! | Bug | 2017-02-20 | Production | Production standardization | Refer to production standardization no STD-015/16-17/000011, system is showing incorrect FAT/SNF on transaction. Also check the stock report- | 2017-02-20 | 5.1.1.37 & 5.1.1.57 | 2017-04-17 | 2017-04-17 | 1) Pending…the mentioned document no is still showing incorrect fat/snf kg 2) system is showing incorrect FAT/SNF/Qty in the stock reco report | Sachin |  | Pending |  | Pending |  | currentky
#REF! | Bug | 2017-03-01 | Purchase | Issue/Return Entry | The screen response of Issue/Return Entry is very slow on VPN. | 2017-03-02 |  |  |  |  | Praveen |  | Pending | Duplicate | Duplicate
#REF! | Change | 2017-03-01 | Purchase | Purchase Order | Pls provide the functionality to short close line item wise purchase order | 2017-03-06 | 5.1.1.57 | 2017-04-17 | 2017-04-17 | Refer to the purchase order POO-003/17-18/000048. 2 line item of this has been short closed. And remaining 2 items have been received in the gate entry no GOT-003/17-18/000156. however, the report is still showing status as open | Naveen |  | Pending | Delivered | Delivered |  | Pending
#REF! | Bug | 2017-03-03 | Material Management | Stock Reco | system is showing incorrect rate in the stock reco report. It is showing different rate than actual rate. Thereby the value of the stock is incorrect in ERP. For example, refer to the item code FG0000081 for 013 location. Date range is 01/03/2017 to 03/03/17. The opening rate is 0.30, however system is issuing at 14.95 in invoice no FDI-013/16-17/008574, at 18.18 in invoice no FDI-013/16-17/008548, and at 14.95 in invoice no FDI-013/16-17/008571 | 2017-03-03 |  |  |  |  | Sandeep |  | Pending |  | Pending
#REF! | Change | 2017-03-06 | Purchase | Purchase Invoice | Pls add qty & UOM on the auto generated debit note description field on the debit/credit note screen. This description field to be printed on the print format after the narration "Being the amt debited on a/c of". Refer to Purchase invoice no PSF-003/16-17/000061 in which 490kg material was short. | 2017-03-06 | 5.1.1.57 | 2017-04-17 | 2017-04-17 | the qty & UOM is not coming in the description of debit/credit note. It should also come to print format. | Sunny |  | Pending | delivered, script is to be run for correction of OLD documents. | delivered | Richa
#REF! | Bug | 2017-03-06 | MCC Procurement | Milk Sample | Sytem is again showing 2 milk sample document pending however SRN & invoices have already been generated against it. Refer to document no MS-415/16-17/000616 & MS-429/16-17/000269. We have faced this issue in the past also. Kindly fix it permanently | 2017-03-06 |  |  |  |  | Prasanjit |  | Pending |  | Done |  |  | correction should be done on live server
#REF! | Bug | 2017-02-20 | Common Services | Excise Summary | 20) While exporting the Excise Summary report, system is changing the date format on output file. In some dates are coming in DD/MM/YY format & some dates are coming in MM/DD/YY format. Also UOM filter is missing on the report -done | 2017-02-20 | 5.1.1.32 & 5.1.1.46 & 5.1.1.57 | 2017-04-17 | 2017-04-17 | Pending…system is not converting data as per item conversion for all the invoices. System is showing invoices in serial. It is jumbling invoices no & date on screen & excel. 2) System is not showing invoices in serial. It is jumbling invoices no & date on screen & excel 3) System still showing incorrect sequence | Mahendra |  | Pending | testing to be done to be delivered | Partially Done
| Bug | 2017-03-30 | Purchase | Misc Sale | The item code which has item type Assets are not coming on misc sale screen. Pls do the needful | 2017-03-30 | [6 empty] | Pending | On Setting Asset Items seen in finder. | Done
#REF! | Bug | 2017-04-08 | MCC Procurement | Milk Sample | Milk sample no MS-415/16-17/000616, MS-428/16-17/000338 & MS-429/16-17/000269 is showing pending, however SRN & bills have already been generated | 2017-04-08 |  |  |  |  | Prasanjit |  | Pending |  | Duplicate
#REF! | Correction | 2017-04-08 | Fresh Sale | Fresh Sale Return | Pls delete fresh sale document no SRFS-013/16-17/000023 dated 01/03/2017 as it was made by mistake | 2017-04-08 |  |  |  |  | Praveen |  | Pending | test and to be delivered | Done
#REF! | Bug | 2017-04-07 | Vendor Management | Vendor Ledger Report | Vendor ledger report is not showing correct data. Refer to VSP04084, system is adjusting credit note amount while running the payment process. Refer to VSP03995 dated 10/03/2017, system is not showing debit adjustment entry, thereby leaving balance in vendor clearing account. Report date 01/02/2017 to 31/03/2017. Pls correct all the VSP for all the locations | 2017-04-08 |  |  |  |  | Rohil |  | Pending |  | Done
#REF! | Bug | 2017-04-08 | Product Sale | MIS Sales Register | MIS Sales register is not showing FAT/SNF for all the document. Refer to document no TI-015/16-17/000001, CSI-015/16-17/000014, CSI-015/16-17/000015, STI-015/16-17/000002. Pls check & correct all the documents | 2017-04-08 |  |  |  |  | Sachin |  | Pending |  | Duplicate
122 | Bug | 2017-04-12 | Purchase | Misc Sale | Misc sale documents are not coming in Pending Document list. Refer to doc no SCP-003/16-17/000016 & do the needful | 2017-04-13 |  |  |  |  | Sunny |  | Pending | test and to be delivered | BI report setting
124 | Bug | 2017-04-13 | Bulk Milk Procurement | Bulk Milk Register | All columns of bulk milk register are not coming in bulk milk register with QC. For example, Standard Rate, Deduction, FAT Rate etc. Since all the new changes is being made in Bulk milk register with QC then Pls make sure that all the columns of Bulk milk register are coming in Bulk milk register with QC report | 2017-04-13 |  |  |  |  | Harish |  | Pending | test and to be delivered | Done
125 | Bug | 2017-04-13 | Purchase | RGP/NRGP | System is not allowing to make the RGP against TIN job work & as per BOM. It is giving the error "incorrect syntax near the keyword and". Pls do the needful | 2017-04-13 |  |  |  |  | Rakesh Mann |  | Pending | To be delivered(tested) | delivered
126 | Bug | 2017-04-13 | Bulk Milk Procurement | Bulk Milk SRN | Bulk Milk SRN print is not coming. It is showing no data found. Refer to Bulk Milk SRN no BMS-003/16-17/031808 | 2017-04-13 |  |  |  |  | Sachin |  | Pending | To be delivered(tested) | delivered
127 | Bug | 2017-04-13 | Bulk Milk Procurement | Bulk Milk SRN |  | 2017-04-13 |  |  |  |  | Harish |  | Pending | To be delivered(tested) | delivered
128 | Bug | 2017-04-13 | Purchase | Purchase Order | When a PO is updated then system does not disable the amendment button automatically, also once a PO is amended then if some other user is opening the same PO then he is also able to make the amendment even if amendment rights have not been given to user | 2017-04-13 |  |  |  |  | Naveen |  | Pending | To be delivered(tested) | delivered
#REF! | Change | 2017-04-13 | Dairy Production | Production Reports | All the production reports, Sale Register & Purchase register should have UOM filter & default UOM check box. If the default UOM check box is ticket then system to show the report in default UOM just like stock reco | 2017-04-13 |  |  |  |  | Sandeep |  | Pending |  | WIP
#REF! | Change | 2017-04-13 | Dairy Production | Production Reports | Report required for difference in Standard Vs Actual fat/snf. The format is being sent by email | 2017-04-13 |  |  |  |  | Sandeep |  | Pending |  | WIP
#REF! | Change | 2017-04-13 | MCC Procurement | MCC Material Sale | the narration which is entered on the mcc material sale document is not going to sale register, general ledger & trial balance. Pls do the needful | 2017-04-13 |  |  |  |  | Rohil |  | Pending | to be checked to be delivered | Done
#REF! | Change | 2017-04-15 | General Ledger | General Ledger Account | Once a GL account is made control account, it is not allowing to make it a normal account for making manual journal entries. Pls provide the functionality to uncheck control account tick as & when required. | 2017-04-17 |  |  |  |  | Preeti |  | Pending | As discussed with Rakesh Sir this will not be provided. | As discussed with Rakesh Sir this will not be provided.
#REF! | Bug | 2017-04-17 | Common Services | Contra Vouchers | The uploader of the contra voucher screen is not working. Pls find attached the format & arrange to correct it | 2017-04-17 |  |  |  |  | Gaurav |  | Pending | Check with Richa | Done
138 | Bug | 2017-04-19 | MCC Procurement | Village difference report | In the village differnce report, All the Route information to be fetched from Masters only. Presently, system is showing some route information from tranaction and some from Masters | 2017-04-20 |  |  |  |  | Prasanjit |  | Pending | to be checked to be delivered | done
140 | Bug | 2017-04-19 | MCC Procurement | Replication | Fat & SNF is being replicated in Rate and amount column on the server in case of farmer data. | 2017-04-20 |  |  |  |  | Prasanjit |  | Pending | ok | Done
141 | Bug | 2017-04-19 | MCC Procurement | Tanker Dispatch Return | System does not free the tanker after tanker dispatch return. The tankrer remains unavailbe for transaction | 2017-04-20 |  |  |  |  | Prasanjit |  | Pending | Needs to be checked | Done
142 | Bug | 2017-04-19 | MCC Procurement | MP Master | Bank code , Bank name, Ifsc code are not being uploaded through uploader of MP master | 2017-04-20 |  |  |  |  | Prasanjit |  | Pending | to be checked to be delivered | Done |  |  | done
143 | Bug | 2017-04-20 | Common Services | Bulk Posting | While clicking on unposted document in the Bulk Posting - all modules report, we are getting permission denied error. Pls do the needful | 2017-04-20 |  |  |  |  | Sunny |  | Pending | To be delivered(tested) | Done |  |  | done
144 | Bug | 2017-04-20 | Material Management | Assembly/Disassembly | System is making assembly/disassembly document in the current date instead of date selected by user. The document no is also coming for the current month. System is not considering the UOM conversion. Pls check | 2017-04-20 |  |  |  |  | Pawan |  | Pending |  | Done |  |  | done
145 | Bug | 2017-04-20 | Purchase | Purchase order | The discount amount field is disabled in Merchant Purchase Order/Purchase order. Pls check | 2017-04-20 |  |  |  |  | Raman |  | Pending | To be delivered(tested) | Done |  |  | done
#REF! | Bug | 2017-03-01 | Production | Production entry | System is showing incorrect FAT/SNF KG in the production entry no. refer to entry no PE-003/16-17/000978. pls correct all the entries & item codes. pls also correct stock reco & production report | 2017-03-02 | 5.1.1.37 | 2017-03-20 | 2017-03-20 | Pending…the mentioned document no is still showing incorrect fat/snf kg | Sandeep |  | Pending
#REF! | Bug | 2017-04-07 | Production | Item Consumption Report | item consumption report is not showing FAT/SNF and rate of all the materials. Refer to the batch order no BO-003/16-17/07/000003 & standardization no STD-003/16-17/001404 in which 824kg of item code SF000020 was consumed. However, item consumption report is not showing fat/snf qty & rate. pls check & correct all the item code | 2017-04-08 |  |  |  |  | Auditor |  | Pending
1 | Bug | 2017-04-13 | Fresh Sale | Price Master | system is not allowing to close posted price master in fresh sale neither it is allowing to save two price master in same date. Pls check | 2017-04-13 |  |  |  |  | Prakash |  | Pending
1 | Bug | 2017-04-13 | Fresh Sale | Fresh Invoice | system created duplicate fresh invoice against dispatch no FDI-003/16-17/123560 to FDI-003/16-17/123612. These invoices have been cancelled by making the document amount zero but print format is still reflecting total amount & the narration "Cancelled due to duplicate entry". Pls do the needful | 2017-04-13 |  |  |  |  | Harish |  | Pending
1 | Change | 2017-04-13 | General Ledger | GL Reports | Pls Provide IND AS tick on General ledger report, P&L and Balance sheet filter. The functionality to be same as Trial balance | 2017-04-13 |  |  |  |  | Preeti |  | Pending | done |  |  |  | done
1 | Change | 2017-04-13 | Dairy Production | Production Reports | Pls provide a summary level report in the item consumption report. The summary should be plant wise production item wise material consumed items. Format is being forwarded by email | 2017-04-13 |  |  |  |  | Sandeep |  | Pending
1 | Bug | 2017-04-19 | MCC Procurement | Village Data | In the village data screen, system is picking the wrong price chart if the rate is effected from the evening | 2017-04-20 |  |  |  |  | Prasanjit |  | Pending | to be checked to be delivered |  |  |  | pending
1 | Bug | 2017-04-20 | Payroll | Salary Generation | Refer to salary generation doc no SALGEN/17-18/000001 to SALGEN/17-18/000006. these document belongs to march 2017, however system is making of document no of 2017-18 period. Pls check | 2017-04-20 |  |  |  |  | Dhananjay |  | Pending |  |  |  |  | done
#REF! | Change | 2017-04-22 | Vendor Management | AP invoice Entry | Below changes are required in the AP invoice entry uploader for updating employee wise salary in ERP 1) Provision for capturing 25 GL accounts. Current uploader is only taking five GL account maximum 2) Provision for GL account wise Debit/Credit. | 2017-04-22 |  |  |  |  | Harish |  | Pending |  |  |  |  | done
pending
ok /tested
pending for development

## Sheet1
S No | Type | Request Date | Module | Screen | Request Description | Date of Assignment to Tecxpert | Delivered Exe No | Delivered Exe Date | Testing Date | Testing Remarks | User Name | User Confirmation date | Status | Status Tecxpert | Status on 28/04/2017 |  | Kwality Remarks | tester remarks
#REF! | Bug | 2017-02-20 | Production | Production standardization | Refer to production standardization no STD-015/16-17/000011, system is showing incorrect FAT/SNF on transaction. Also check the stock report- | 2017-02-20 | 5.1.1.37 & 5.1.1.57 | 2017-04-17 | 2017-04-17 | 1) Pending…the mentioned document no is still showing incorrect fat/snf kg 2) system is showing incorrect FAT/SNF/Qty in the stock reco report | Sachin |  | Pending |  | Pending |  |  | currently working fine previous data should be correct on live server
#REF! | Bug | 2017-03-03 | Material Management | Stock Reco | system is showing incorrect rate in the stock reco report. It is showing different rate than actual rate. Thereby the value of the stock is incorrect in ERP. For example, refer to the item code FG0000081 for 013 location. Date range is 01/03/2017 to 03/03/17. The opening rate is 0.30, however system is issuing at 14.95 in invoice no FDI-013/16-17/008574, at 18.18 in invoice no FDI-013/16-17/008548, and at 14.95 in invoice no FDI-013/16-17/008571 | 2017-03-03 |  |  |  |  | Sandeep |  | Pending |  | Pending
#REF! | Change | 2017-03-06 | Purchase | Purchase Invoice | Pls add qty & UOM on the auto generated debit note description field on the debit/credit note screen. This description field to be printed on the print format after the narration "Being the amt debited on a/c of". Refer to Purchase invoice no PSF-003/16-17/000061 in which 490kg material was short. | 2017-03-06 | 5.1.1.57 | 2017-04-17 | 2017-04-17 | the qty & UOM is not coming in the description of debit/credit note. It should also come to print format. | Sunny |  | Pending | delivered, script is to be run for correction of OLD documents. | delivered | Richa |  | working fine
#REF! | Bug | 2017-02-20 | Common Services | Excise Summary | 20) While exporting the Excise Summary report, system is changing the date format on output file. In some dates are coming in DD/MM/YY format & some dates are coming in MM/DD/YY format. Also UOM filter is missing on the report -done | 2017-02-20 | 5.1.1.32 & 5.1.1.46 & 5.1.1.57 | 2017-04-17 | 2017-04-17 | Pending…system is not converting data as per item conversion for all the invoices. System is showing invoices in serial. It is jumbling invoices no & date on screen & excel. 2) System is not showing invoices in serial. It is jumbling invoices no & date on screen & excel 3) System still showing incorrect sequence | Mahendra |  | Pending | testing to be done to be delivered | Partially Done |  |  | n ot in exe
#REF! | Change | 2017-04-13 | Dairy Production | Production Reports | All the production reports, Sale Register & Purchase register should have UOM filter & default UOM check box. If the default UOM check box is ticket then system to show the report in default UOM just like stock reco | 2017-04-13 |  |  |  |  | Sandeep |  | Pending |  | WIP
#REF! | Change | 2017-04-13 | MCC Procurement | MCC Material Sale | the narration which is entered on the mcc material sale document is not going to sale register, general ledger & trial balance. Pls do the needful | 2017-04-13 |  |  |  |  | Rohil |  | Pending | to be checked to be delivered | Done |  |  | need to clerify to harish
#REF! | Bug | 2017-04-19 | MCC Procurement | Tanker Dispatch Return | System does not free the tanker after tanker dispatch return. The tankrer remains unavailbe for transaction | 2017-04-20 |  |  |  |  | Prasanjit |  | Pending | Needs to be checked | Done |  |  | working fine
#REF! | Bug | 2017-03-01 | Production | Production entry | System is showing incorrect FAT/SNF KG in the production entry no. refer to entry no PE-003/16-17/000978. pls correct all the entries & item codes. pls also correct stock reco & production report | 2017-03-02 | 5.1.1.37 | 2017-03-20 | 2017-03-20 | Pending…the mentioned document no is still showing incorrect fat/snf kg | Sandeep |  | Pending |  |  |  |  | not done
#REF! | Bug | 2017-04-07 | Production | Item Consumption Report | item consumption report is not showing FAT/SNF and rate of all the materials. Refer to the batch order no BO-003/16-17/07/000003 & standardization no STD-003/16-17/001404 in which 824kg of item code SF000020 was consumed. However, item consumption report is not showing fat/snf qty & rate. pls check & correct all the item code | 2017-04-08 |  |  |  |  | Auditor |  | Pending
#REF! | Bug | 2017-04-13 | Fresh Sale | Price Master | system is not allowing to close posted price master in fresh sale neither it is allowing to save two price master in same date. Pls check | 2017-04-13 |  |  |  |  | Prakash |  | Pending
142 | Change | 2017-04-13 | Dairy Production | Production Reports | Pls provide a summary level report in the item consumption report. The summary should be plant wise production item wise material consumed items. Format is being forwarded by email | 2017-04-13 |  |  |  |  | Sandeep |  | Pending
#REF! | Change | 2017-01-15 | Common | All | Prompt message to clear all the pending transaction on the last day of the month. | 2017-01-15 | 5.1.1.37 | 2017-03-20 | 2017-03-20 | Pending…system is not allowing to give the declaration of the pending document. It is showing DB Null error which submitting the declaration. Moreover, it is not showing all the documents of the user. The report is also not there | SK Gupta Sir |  | Pending |  | Done | Kunal | Pending | pending
#REF! | Change | 2017-01-15 | Common | All | Screen for declaration of pending documents on monthly basis | 2017-01-15 | 5.1.1.57 | 2017-04-17 | 2017-04-17 | While log in, system is not showing any declaration screen | SK Gupta Sir |  | Pending |  | Done | Kunal | Pending | pending